Syria Drought Response Plan

2009-2010

MID-TERM REVIEW

A Roman well, rehabilitated by UNDP, gives water to parched land in drought-affected eastern Syria

(Photo by Ali Kayali UNDP)

United Nations

February 2010

TABLE OF CONTENTS

1.	EXECUTIVE SUMMARY	1

Table I.	Summary of Requirements (grouped by cluster)	2

Table II.	Summary of Requirements (grouped by priority)	2

Table III.	Summary of Requirements (grouped by appealing organization)	3

2.	CHANGES IN THE CONTEXT, HUMANITARIAN NEEDS AND RESPONSE	4

2.1	Rain pattern and prospects for the 2010 agricultural season	4

2.1.2	Nutrition	5

2.1.3	Migration and school dropout	6

3.	RESPONSE TO DATE, AND UPDATED STRATEGIC AND SECTORAL RESPONSE PLANS	7

3.1	Funding update	7

3.2	Updated Sector Response Plans	11

3.2.1	FOOD	11

3.2.2	WATER AND SANITATION	13

3.2.3	HEALTH AND NUTRITION	13

3.2.4	EDUCATION	14

3.2.5	AGRICULTURE AND LIVELIHOODS	15

ANNEX I.	FULL PROJECT LIST AND FUNDING TABLES	17

ANNEX II.	ACRONYMS AND ABBREVIATIONS	21

# 1.	EXECUTIVE SUMMARY

A third consecutive year of drought has hit north-eastern Syria.  According to Government and UN estimates, 1.3 million inhabitants are affected and 800,000 severely affected, over 95% of whom live in the three governorates of Al-Hassake, Dayr az Zawr and Ar-Raqqa.  The effects of the drought are being exacerbated by the impact of high food and fuel prices, and the global financial crisis.  The result is a dramatic decrease in communities’ resilience and coping capacity.  The rural population directly affected by the drought has lost almost all sources of livelihood and faces extreme hardship.

Up to 80% of those severely affected live mostly on a diet of bread and sugared tea, which is not enough to cover daily calorific and protein needs for a healthy life.  Direct consequences of the drought include decreased food intake, reduced capacity to restore livelihoods, massive internal displacement towards cities, and alarming school dropout rates in some areas.  Those affected cannot sustain or restore their livelihoods without emergency food assistance that is coupled with additional assistance, such as potable water, farming inputs and animal feed.

In response to this crisis, and following the Government’s request, the United Nations Country Team (UNCT) prepared the UN Syria Drought Response Plan (SDRP) in August 2009.  The SDRP aims to supplement and augment the response orchestrated by the Government of Syria.  The SDRP aims to address emergency humanitarian needs and reduce the drought’s impact on the most vulnerable –  300,000 people of the 800,000 severely affected.  The SDRP’s duration is linked to the agricultural calendar, with international assistance necessary until the next crops are harvested in May and June 2010.

Insufficient donor response is the most significant obstacle to implementing planned actions in the 2009/2010 SDRP.  By the end of 2009, the appeal was only 14% funded. In response, the UNCT sought emergency funding from the UN Central Emergency Response Fund (CERF).  CERF is now the single largest donor to the SDRP.  Nine SDRP projects totaling 22% of the Response Plan’s original requirements have received no funding.

This document allows for new analysis of humanitarian needs in view of the continuing drought.  It includes new rainfall data that gives a more positive outlook for an improved agricultural season during the 2009/2010 winter than was initially forecast.  However, the drought-affected population will remain in dire need of food, agriculture and other assistance until mid-2010, when crops are expected to mature.  Although the majority of planned response actions in the SDRP are still urgently required, some activities in this Mid-Term Review (MTR) have been reduced as the time for possible implementation is now only six months.

The UNCT established a Food Security Coordination Group.  Agencies participating in the SDRP are focusing their attention on the Al-Shaddadi district of Hassake Governorate as the area with the highest migration rate (see map on page 4).  This district will benefit from the coordinated activities of the agencies participating in the SDRP, as well as by key Government agencies.  All UN and Government of Syria stakeholders have agreed to target the same geographical areas as selected on the basis of joint criteria, and have set up effective coordination mechanisms.

The UN and its partners seek donor funding for continued humanitarian activities in north-eastern Syria to the revised amount of US$43,687,572 for the period December 2009 to June/July 2010.  This amount constitutes a 17.5% decrease from the SDRP's original requirements of $52,938,616.

#### Table I.	Summary of Requirements (grouped by cluster)

#### Table II.	Summary of Requirements (grouped by priority)

#### Table III.	Summary of Requirements (grouped by appealing organization)

# 2.	CHANGES IN THE CONTEXT, HUMANITARIAN NEEDS AND RESPONSE

## 2.1	Rain pattern and prospects for the 2010 agricultural season

In 2007/2008, Syria faced the worst drought in over four decades due to a severe shortage of rainfall.  The pattern of poor rainfall continued in 2008/2009, furthering the drought and particularly affecting the east of the country (Al Hassakeh, Deir Ezzor and Ar Raqqa).  The highest amount of rainfall on a long-term basis is traditionally received in Edlib (500mm) and Homs (420mm), followed by Aleppo (340mm) and Hama (330mm; see below Figure 1).

However, this dramatically changed during the 2007/2008 and 2008/2009 seasons.  During these two years, Al Hassakeh, Deir Ezzor and Ar Raqqa received much-reduced rainfall, especially in 2007/2008, with shortfalls of 66%, 60% and 45%, respectively.  Zones 4 and 5 of these governorates were seriously affected, in particular because of the practice of rain-fed cropping in these governorates.  The most affected were Al Hassakeh, Deir Ezzor and Ar Raqqa.  Only about 50% of the long-term average was received in these areas.  Rural Damascus received 69% of the long-term average.  The least-affected areas were Hama and Homs, which received 80% and 84% of the long-term average respectively.

Figure 1: Rainfall received in various governorates in 2008/09 as compared

with the 2007/08 season and the long-term average

Drought in north-eastern Syria and its impact on vulnerable populations

Since 2006, three consecutive years of drought have affected Syria.  The 2007/2008 drought was the worst in 40 years and had a wider geographical reach.  However, the 2008/2009 drought hit a population already suffering from the impact of previous droughts, from economic difficulties due to high global food and fuel prices, and from the financial crisis.  On average, income for these populations has decreased by over 90% over the past few years and, even worse, their assets and sources of livelihood have been lost or irremediably compromised.  Numerous farmers have had no crops for two consecutive years and lost seeds.  Many medium- and small-scale herders have lost over 80% of their flocks due to lack of pasture and fodder.

The population is suffering from poor food consumption, insufficient supplies of potable water and inadequate health services.  Over 80% of the families visited during field assessments revealed that their daily food intake was composed mostly of bread and sugared tea, with no difference between children’s and adults’ intakes.  Milk is no longer available for children.  Most families have not consumed animal proteins in months.  Daily meals have been reduced from three to one for adults, and to two for children.  It is evident that this diet will lead to significant nutrition problems in all age groups of the most severely affected population.  Although it is difficult to disaggregate the coping strategies between men and women, the latter see their weddings delayed or are married at early age, to reduce their families’ expenditures, or to have their husband’s family provide their nutrition.  This is in addition to reduced quality and quantity of food intake.

### 2.1.2	Nutrition

In this context, malnutrition is an increasingly serious concern and efforts are being made to establish a nutrition baseline and monitoring system.  The 2007 Multiple Indicator Cluster Survey shows that the main nutrition indicators for children under-five were higher in the north-eastern governorates compared with the national average.  The nutritional status of 2006 has deteriorated due to the severe drought.  Recent data collected at the Primary Health Care (PHC) centres of Al-Hassake, Dayr az Zawr and Ar-Raqqa indicate a drastic increase in nutrition-related diseases between 2006 and 2009.  Based on information from sentinel sites, the recently established nutrition surveillance system indicates a high rate of anaemia (42%) for children aged 6 to 12 months in Al-Raqqa governorate.  This is likely due to poor complementary feeding practices and poor food consumption due to the prolonged drought.

### 2.1.3	Migration and school dropout

For some male family members, seasonal labour migration is a common practice for poor households of the steppe and arid zone.  However, sharp impoverishment in recent years has resulted in the migration within the country of entire families from 160 villages to the periphery of cities.  Since early 2009, the migration pattern has increased dramatically: 65,000 families have already left their villages.  From this total, 35,000 are from Al-Hassake and 30,000 from Dayr az Zawr, Ar-Raqqa and Aleppo.  This drastic move has not saved these internally displaced families from further hardship and destitution.  Instead, they have lost their social ties and are often exploited at below-market labour rates.  It has also further increased the strain on the limited job market, resources and public services, which were already affected by the presence of approximately one million Iraqi refugees.

Under such conditions, school dropout rates are high and enrolment has significantly declined.  According to the Joint United Nations Assessment Mission (JNAM) results, enrolment in some schools in north-eastern Syria has decreased up to 80%.  Children are not attending school because they are migrating with their families, the family can no longer afford school costs, or because they are sent to work to provide some income for the family.

# 3.	RESPONSE TO DATE, AND UPDATED STRATEGIC AND SECTORAL RESPONSE PLANS

## 3.1	Funding update

The SDRP estimated that out of 1.3 million people affected by the drought, some 800,000 have been severely affected and 300,000 are considered as highly vulnerable.  So far, the assistance channelled through the Response Plan targeting 300,000 people through food distribution and other measures has reached only 10,000 farmers (144,000 people).  This is due to low funding and delays in channelling funds to World Food Programme (WFP) and UNICEF.

As of 22 February 2010, the SDRP was only 19% funded ($8.4 million).  CERF has been the single largest donor to the Response Plan, having contributed $3,287,464, or 38% of total funding to date.  The UNCT has decided to request further emergency support from CERF only in a situation when dramatic funding levels did not allow time-critical interventions to begin.

The Government has also provided significant support to Food and Agriculture Organization (FAO) projects implemented in the SDRP framework.  This assistance has taken a form of direct subsidies for seeds and fodder purchased by FAO.  In addition, governmental in-kind contributions include storage facilities at distribution centres, staff labour and local operational costs.  The Government’s contribution to the SDRP is estimated at $726,000.

Of the agencies participating in the SDRP, WFP has received the most funds in terms of dollars contributed ($5.4 million) and percent funded (24% of revised requirements).  This will allow WFP to undertake the first cycle of food distribution for 300,000 people in February 2010, with particular attention to Al-Shaddadi district.  Furthermore, 6,000 children under-five and 2,000 pregnant and lactating women will also receive supplementary feeding assistance.

With the effects of the drought not only devastating livelihoods and endangering nutritional status, forcing many families to migrate to cities, the WFP School-Feeding Project has proved to be a very effective strategy.  WFP reported that the schools assisted under this programme are witnessing increased enrolment and attendance, and a stabilized dropout rate.  In Markaz Al-Shaddadi, by considering schoolchildren as direct recipients of the food assistance, WFP has been able to contribute to the ultimate goal of preventing internal displacement of entire families and keeping children out of the labour market.

Second is FAO with $2.5 million received, constituting 22% of its revised requirements.  Importantly, FAO time-critical interventions for farmers and herders received only 16.9% of required funding.  Due to agricultural requisite needs, FAO started to implement seed distribution before WFP and UNICEF began implementing their projects.  Agencies participating in SDRP agreed to focus on Al Shadaddi (Hassake Governorate) because it was recognized as the area most affected by the drought.  As part of this focus, UN agencies established a coordination group to improve the humanitarian impact of the funds channelled through SDRP.  FAO shared lists used for seed distribution with other UN agencies, which WFP will consider for its targeting in zone 4 (farming areas) which constitutes 28% of the project’s targeting.

UNICEF activities have received 15% of funding.  UNDP is funded at 5% whilst of some considerable concern, IOM, QRCS and WHO have not received any funding at all for projects in the SDRP.  Through CERF funding, UNICEF is undertaking a therapeutic feeding programme in Al-Shaddadi.  The project includes providing plumpy’nut, supplies to 10 targeted health centres through support to MoH staff, and providing anthropometric measuring equipment and recording forms.  The project will not only improve the nutritional status of most vulnerable children but will also enable growth monitoring (height and weight measuring), which feeds into UNICEF efforts to expand the nutrition surveillance system to the north-eastern governorates.

UNDP completed the assessment for checking the validity of rehabilitating roman wells in the north-eastern region.  The allocated amount was enough to rehabilitate 22 wells in the eastern region, distributed as follows:

- Ten in Der Azzour;

- Seven in Raqqa;

- Five in Hassakeh.

Rehabilitation will provide 11,000 people with potable water and allow them to provide drinking water to 30,000 livestock.  Such an intervention can encourage people to return to their villages in the Badia.

Response to date by the United Nations and partners

| SDRP Objective | Achieved as of MTR |
| --- | --- |
| Immediate humanitarian aid | Food assistance to 300,000 most vulnerable people | WFP will have first distribution in the second week of February 2010 |
|  | Improving water supply in water-stressed communities | UNDP is rehabilitating 22 wells |
|  | Supporting health assistance and nutrition monitoring | Equipped ten PHC centres with malnutrition-surveillance-measure tools |
|  | Providing agricultural inputs to herders to allow them to preserve their livelihoods and re-establish their herds and seeds to small farmers | 10,000 destitute small-scale wheat and barley rain-fed farmers with total population of 144,000 including children and women. |
| Livelihood recovery | Supporting activities in providing skills and income support to the most vulnerable community in the north-eastern region to build community resilience to drought | No funding received |
| Improved resilience against new drought | Decreasing the population’s dependency on agricultural jobs by encouraging creation of other resources of employment | No funding received |
|  | Implementing new agricultural solutions to enhance drought resilience | No funding received |
|  | Building national capability to implement the national drought strategy | No funding received |
|  | Developing a national early warning system (EWS) | $476,150 |

Government of Syria’s response

The Government of Syria has provided assistance to the most vulnerable segment of the drought-affected population since 2008.  However, the scope and severity of the crisis has overstretching the Government’s response capacity.  The development and issuance of the SDRP in August 2009 was aimed at supplementing and enhancing the Government’s assistance to the most affected population.

Since 2008, the Government has launched several relief interventions across all sectors, from food assistance, to support to farmers and herders, and wider measures are planned for 2009 and 2010.  By July 2009, the Government had provided 5,600 MT of food assistance to 96,660 households, or to about 500,000 people living in Al-Hassake, Dayr az Zawr, Ar-Raqqa, Homs and Rural Damascus.

In August 2009, the Government took tangible steps on drought-mitigation policies by adopting a National Drought Strategy with relative implementation guidelines, and by creating an Inter-Ministerial Committee directly headed by MoAAR.  A new Directorate for Drought Management is being established to identify drought-prone areas, build a new early warning system and set up emergency plans.

Following a ministerial field assessment mission in June 2009, a set of measures was issued to mitigate the drought’s effects.  The recommendations included the following:

- Establish a fund for the drought-affected population amounting to 1% of the country’s agricultural production value;

- Deliver seeds to farmers and fodder to small-scale herders;

- Increase the purchase price of cereal crops and renegotiate farmers’ loans over a nine-year period with one year of grace;

- Launch a new programme of loans;

- Deliver licenses to 13,000 existing unauthorized wells.

As well as implementing the tenth Five-Year Development Plan, the Government has undertaken studies on non-agricultural solutions and on creating a favourable environment for investment in north-eastern Syria.  These studies include feasibility studies for tourism development and agro-industries, and for transporting water from the Tigris River to the steppe, necessary for the irrigation of some 150,000ha of land in Al-Hassake.  This project is expected to help farmers continue attending to their land, and to create employment opportunities and sources of income for other farmers with no land for most of the agriculture season.  This will help improve the rural population’s livelihoods.

Government institutions are present in the drought-affected areas.  They include, among others, local administrations (governorates), local representations of the Ministries of Agriculture and Irrigation, the central-level Badia Commission and the SPC.  These institutions are strong in terms of staff, skills and follow-up work on government directives and resources.  However, they require further training and improvement in addressing the various dimensions of the crisis.  Despite efficient logistics capacity that is able to reach the most remote areas, quick response and rapid increase in capacity needs to be reinforced.  There is also a strong need for capacity-building to create more efficient inter-institutional coordination, participation and a bottom-up approach, working with civil society and international partners.

Updated strategic priorities

Due to low levels of funding, many SDRP activities were not implemented in time.  Although the first rains gave hope to a promising agricultural season, the humanitarian needs resulting from a three-year drought in eastern Syria are not expected to relent, at least until the yields in mid-2010.  Even if farmers can re-start their agricultural work during the winter, they and the herders will need food assistance until the crops mature between May and June 2010.  Their precarious situation will require a continuation of water and sanitation, health and nutrition, and education and livelihoods interventions until the end of the SDRP time frame in mid-2010.  In this respect, the SDRP strategic priorities remain valid at the time of the MTR.  SDRP assistance is aimed at enhancing and augmenting the Government’s response to the disaster.  The assistance focuses on three main areas:

- Provide humanitarian assistance to the severely drought-affected population in north-eastern Syria and Badia, in support of measures taken by the Government of Syria;

- Strengthen drought-affected communities’ resilience to future drought and climate change; provide immediate assistance in the return process of the drought-affected population; ensure their socio-economic stability;

- Provide immediate assistance in the return process of the drought-affected population to their villages/places in the Hassake Governorate and others, accompanied by stabilization measurements to avoid the reoccurrence of such movement and working to ensure sustainable solutions.

Improved coordination of assistance

To maximise the use of limited resources received to date, the agencies participating in the SDRP are focusing their attention on the Al-Shaddadi district of the Hassake Governorate as the area of the highest migration rate (see map page 4).  This district has and will continue to benefit from coordinated activities by WFP (supplementary and general food assistance), FAO (distribution of seeds and agricultural inputs), UNICEF (nutrition) and UNDP (well rehabilitation).  The agencies are acting in synergy with Government counterparts, represented by the SPC, the General Badia Commission, the MoE, MoAAR and MoH.  All UN and Government of Syria stakeholders have agreed to target the same geographical areas as selected on the basis of the criteria described below.  In view of limited resources, participating agencies have formed a working group to ensure best possible coordination of the assistance to the Al-Shaddadi district and other most vulnerable areas.  To map the food assistance provided by all humanitarian actors in drought-affected areas, WFP is involved in a coordination meeting.

SYRIA DROUGHT RESPONSE PLAN: HOW THE ASSISTANCE IS TARGETED Agencies participating in the SDRP are employing three levels of beneficiary targeting in eastern Syria: Geographical-level targeting: The operation is being implemented in the agro-climatic zones receiving less than 250mm of annual rainfall (agro-climatic zones 4 and 5) of Al-Hassake, Ar-Raqqa and Dayr az Zawr Governorates, with the exception of the Euphrates River belt and urban areas. It will focus on those districts that experienced a high level of deterioration of the vegetation cover during the past three years, as indicated by an analysis of the Normalized Difference Vegetation Index. Community-level targeting: In agro-climatic zone 5, the General Badia Commission will provide WFP and other agencies with lists of the most vulnerable among the most affected communities, based on the levels of crop failure, livestock depletion, lack of potable water, remoteness from public services, levels of internal displacement and school dropout rates. Al-Shaddadi district in Al-Hassake Governorate has been prioritized by the UN agencies (UNICEF, FAO and WFP) for urgent assistance through CERF funding. Following the success of the school-feeding project in Al-Shaddadi District, WFP will distribute food assistance through primary schools, making school-age children the “direct recipients” of the family ration entitlement. This is expected to prevent drop out, decrease child labour, discourage the displacement of entire families, and encourage families to return to their villages and attend to their land. Household-level targeting: Targeted beneficiaries will be the most vulnerable among the rural households of severely affected small-scale farmers and/or herders who lost at least two consecutive rain-fed crops and/or over 80% of their animal stock, with no access to irrigation and no alternative sources of income. Among these households, those with children under-five, as well as pregnant and lactating women, will be targeted for supplementary feeding in Markaz Al-Shaddadi Sub-District, where UNICEF will implement the therapeutic feeding programme. In agro-climatic zone 5, the General Badia Commission identified households using a community-participatory approach. Once lists are received, the country office will proceed with a verification exercise based on a random selection of locations and families. This is to ensure that geographical, community and household selection has been properly applied in January 2010.

## 3.2	Updated Sector Response Plans

### 3.2.1	FOOD

| Indicator | Target | Achieved as of MTR |
| --- | --- | --- |
| Number of beneficiary families receiving assistance by distributing agency | 300,000 people – WFP | WFP will start implementing its project in the second week of February |
|  | 50,000 families – QRCS | No Funding Received |
| Caloric value of the ration distributed | 1,200kcal/day | 1,600kcal/day (75% of nutritional requirements) 1,000kcal/day as supplementary feeding for children under-five and pregnant women |
| Caloric value of an average diet of drought-affected population (based on a diet consisting of bread and tea with sugar) | 980kcal/day (calculated by WFP) | WFP will start applying its project in the second week of February |
| Migration levels | 40,000 people (approx. 5,000 families) | No funding received |
| Numbers of schools targeted | 29 | Due to lack of funds, schools can only be covered for the first distribution |
| Number of school-feeding beneficiaries | 30,000 children | 4,000 children as recipients for their family rations (total 45,000 people) |

The 2009 Joint Needs Assessment Mission revealed that the rural population are directly and severely affected by drought.  They suffer from poor food intake, insufficient supplies of potable water and inadequate health services.  Their current diet is characterized by a scarcity of energy and proteins, absence of vitamins and fats, and an unbalanced ratio of calories from carbohydrates and fat.  The nutritional status is deteriorating, especially for children under-five.  Since the onset of the drought, there has been an increase in the number of children visiting health centres for waterborne and nutrition-related diseases.

WFP will provide food assistance to 300,000 beneficiaries for eight months and until the next crop season in July 2010.  The intervention will complement the present diet and provide 75% of nutritional requirements instead of 55% initially planned.  This will allow people to recover from an exhausted nutritional status, which results from a lack of proteins, calories and vitamins.  The intervention will cover the severely affected populations in Hassake, Dayr az Zawr, and Ar-Raqqa.  In the Al-Shaddadi District, 45,000 beneficiaries out of 300,000 will be reached through food distribution to 4,000 school-age children.  Priority will be given to vulnerable groups, such as women-headed households, school children at risk of dropping out of school and engaging in income-generating activities, elderly and sick people, and herders and farmers who have lost most of their productive assets.  With the exception of a higher level of nutritional needs covered by WFP food rations (75% instead of 55% initially planned), other SDRP sector objectives remain valid at the time of the MTR.

The food assistance will complement beneficiaries’ current daily ration by providing an average of 1,584kcal per day, per person.  The ration will cover 75% of energy, 92% of protein and 87% of fat requirements in addition to calcium, iodine, iron and other micronutrients.

To redress the nutritional deficiency, the basket will include cereals, pulses, vegetable oil and salt.  The monthly ration for each beneficiary will consist of 8.75kg of cereals (including 2.5kg of fortified wheat flour), 2.5kg of pulses, one litre of vegetable oil and 25g of salt.  The supplementary feeding in Al-Shaddadi district will foresee a monthly distribution of 0.6kg of Ready-to-Use Supplementary Food (RUSF) to children between six months and two years old.

A balanced diet and a diversified food basket will be distributed to households every two months.  This is due to the large family size in the targeted areas (approximately ten members), and to avoid a monotonous diet.  The first distribution cycle will take place in February 2010 and the last one in July 2010.

| COMPOSITION OF WFP FOOD ASSISTANCE FOR DROUGHT-AFFECTED POPULATION |  | SUPPLEMENTARY FEEDING FOR CHILDREN TWO TO FIVE YEARS OLD AND PREGNANT AND LACTATING WOMEN |
| --- | --- | --- |
| Commodity | Daily ration (grams) | Energy kcal per day | Monthly ration (kg) |  | Commodity | Daily ration (grams) | Energy kcal per day | Monthly ration (kg) |
| Cereals (50% rice and 50% bulgur wheat) | 208.33 | 740 | 6,250 |  | Blended food (wheat-soy blend) | 166.66 | 667 | 5.00 |
| Pulses (50% lentils and 50% beans) | 83.33 | 280 | 2,500 |  | Sugar | 16.66 | 67 | 0.5 |
| Fortified wheat flour | 83.33 | 292 | 2,500 |  | Vegetable oil | 30.7 | 272 | 0.921 |
| Vegetable Oil | 30.7 | 272 | 0,921 |  | Total | 214 | 1006 | 6.42 |
| Iodized salt | 4.16 | - | 0,125 |  |  |  |  |  |
| Total | 410 | 1584 | 12.30 |  |  |  |  |  |

| SUPPLEMENTARY FEEDING FOR CHILDREN SIX MONTHS TO TWO YEARS OLD |
| --- |
| Commodity | Daily Ration gram per day | Energy Kcal per day | Monthly Ration kg per month |
| Nutributter | 20 | 247 | 0.6 |

Until recently, Syria had no systematic nutritional data collection in place and concern over the nutritional status of the population was not a priority for the Government.  UNICEF and WFP have jointly raised the Government’s awareness of this issue, resulting in a newly established nutritional surveillance system by the Government, with UNICEF technical assistance.  Data from this surveillance system, as well as from the Emergency Food Security Assessment (EFSA) to be undertaken in early 2010, may reveal a higher number of malnutrition cases than those currently estimated.  Subject to these findings, the operation may be realigned accordingly.  WFP is considering the possibility of providing a full ration and/or rapidly scaling up the supplementary feeding component if the prevalence of acute malnutrition reaches a level close to the emergency threshold established by WHO.

Changes to SDRP projects

Due to the late start of the project and the reduction in time from 12 to 8 months, the financial requirements of the WFP food assistance project have decreased to $22,330,337.

In Focus: Assistance to drought victims in Al-Hassake district 2009/Impact of WFP Drought Emergency Operation 10778 Khadija is a Bedouin widow who lives with her four daughters in one of Al-Hassake’s drought-affected villages. The drought has left her with no resources except for the small amount of money that her daughters earned collecting wheat grains. Now, her small girls are the household breadwinners. As it is the harvesting season, they go to the neighbouring fields each morning to collect whatever grains have fallen after wheat harvesting. With their small hands, the girls collect wheat grains from the ground. Without considering the heat or the pain they might experience, their sense of responsibility makes them do their job happily. Once they return home, the eldest daughter, who is disabled, goes to nearby shops with her 1kg or 2kg priceless bag of grains to sell for only 10 to 25 Syrian Pounds (55 cents). She uses this to buy bread. “How glad I was upon hearing about WFP’s food assistance. In fact, I started imagining the food and thinking about that foreseen distribution day.” Khadija said. Today is the fifth day after WFP food assistance distribution. Khadija looks relieved. Her daughters are sitting around her, no more collecting to do even if for a while. Her disabled daughter is at home eating home-made bread with cooked lentils. ”I am grateful for WFP. This food assistance came as a gift from God. It gave us a push of strength to struggle and cope longer. Now, instead of depending on bread as our daily consumed food, I have in my kitchen a number of food items. My daughters are around me playing. They will be given the chance to improve their nutritional status. Honestly, my little girls seem better and so do I. “I ask WFP to continue this food assistance and to help us recover from this drought. My girls used to call their small bag of collected grains the golden bag, and I would also like to call WFP’s food basket the golden collection.” (source: WFP Syria)

### 3.2.2	WATER AND SANITATION

| Indicator | Target | Achieved as of MTR |
| --- | --- | --- |
| Number of small-scale water treatment plants installed | 6 | No funding received |
| Number of reverse osmosis units installed | 2 | No funding received |
| Number of Roman wells rehabilitated | 30 | 22 Roman wells rehabilitated |
| Number of persons with improved access to water | 120,000 | 11,000 |
| Number of water storage tanks installed in schools | 75 | No funding received |

In cooperation with the local community and the resident population, UNDP experts surveyed well sites in the affected area.  The selection criteria were:

- Location;

- Depth;

- Water level;

- Opening and well diameter at various depths;

- Type of road leading to the well;

- Number of beneficiaries and power resources.

Sector activities aim to improve access in quality and quantity to potable water for the most vulnerable and severely affected populations of the north-east.  SDRP sector objectives remain valid at the time of MTR.  Activities include:

- Improving provision of potable water among the affected population, with a view to reducing migration;

- Improving the quality of supplied water and increasing the capacity of the water institutions for water quality management;

- Providing and increasing water amounts to schools, with a view to reducing student dropout rates.

### 3.2.3	HEALTH AND NUTRITION

| Indicator | Target | Achieved as of MTR |
| --- | --- | --- |
| Percentage of pregnant women provided with ferrous folic acid | 100% | No funding received |
| Measles immunization coverage | 95% of children under-five in the drought-affected areas | No funding received |
| Number of centres providing timely reporting on communicable diseases | 100% | No funding received |
| Number of health workers trained on proper growth monitoring | 100% | No funding received |
| Percentage of iron deficiency anaemia in children 6 to 12 years | 10% | No funding received |

UNICEF will provide therapeutic feeding to severely malnourished children under-five using RUSF.  This will be done in collaboration with WFP to ensure the best access and identification of malnourished children, through promotion at food distribution points.  Therapeutic food will be delivered in Al-Shaddadi district.

In 2008, UNICEF established a nutrition surveillance system.  This is gradually expanding and should yield initial enhanced malnutrition data by the beginning of 2010.

At the time of the MTR, SDRP objectives remain valid.  These objectives are:

- Support pregnant and lactating women by providing them with ferrous folic acid tablets and preventing anaemia;

- Where necessary, conduct measles immunization campaigns, especially in peri-urban migrant settlements, and distribute vitamin A;

- Strengthen the surveillance system for communicable diseases;

- Conduct health education and awareness campaigns, and distribute educational materials, hygiene supplies and materials;

- Extend and strengthen the nutrition surveillance, including training of health workers on proper growth monitoring;

- Support emergency departments in health centres and hospitals to manage cases of acute asthmatic attacks and respiratory infections;

- Conduct local survey to estimate the prevalence of anaemia among school children.

There are no changes to SDRP projects in this sector.

### 3.2.4	EDUCATION

| Indicator | Target | Achieved as of MTR |
| --- | --- | --- |
| School dropout rate in the targeted schools | (target to be identified) | No funding received |
| Number of teachers trained on pedagogy of child-friendly school (CFS) | (target to be identified) | No funding received |
| Number of students who received the education kits and attend schools in the drought-affected areas | (target to be identified) | No funding received |
| Number of schools supplied with school supplies and equipment to enrol those immigrant children from the drought-affected areas |  |  |

The extended drought has depleted families’ livelihoods and coping mechanisms to deal with the shortage of food and income.  This has directly affected school enrolment, with high dropout rates in the past two years.  According to a UN needs assessment, enrolment in some schools in eastern Syria has decreased between 70% and 80%.  Some children were taken out of school in April 2008, and hope to return by the end of 2009 or early 2010 if the situation improves.  An example can be seen in Al-Neriiah village: a UN assessment mission found that a school with capacity for 100 students had only 15 students attend during the school year 2008/2009.  A Government report on drought impact in Hassakeh Governorate, prepared in June 2009, states that 19 schools have closed in the districts of Tel Tamer, Al Shadadi, Tal Hamis, Amuda, Kamishli, Ras Al Eim.  In Hassake Governorate, 7,380 children have dropped out of school.  In Dayr Ez-Zawr Governorate (population 1.1 million), at least 13,250 students have dropped out of schools in the 2007/2008 and 2008/2009 academic years.

According to the heads of households interviewed by the UN assessment missions, the necessity to cover families’ daily needs had to be given priority ahead of school attendance.  Many drought-affected households cannot afford to send their children to school due to: (a) financial hardship; (b) increased cost of transportation and distance; (c) migration of children with their families who left the villages to other areas in search of work; (d) employment of children to earn additional income for households, which presently overrides all other priorities because of the question of survival.

In new and spontaneous settlements in western Syria inhabited by migrants from drought-affected areas, children work with their parents in agriculture fields to support their families.  Many of them do not attend school.  The living conditions in camps are not suitable for studying as all the family members share one tent.

Although this sector had not received funds at the time of the MTR, the sector objectives remain valid.  These objectives are:

- Reduce high dropout rates;

- Build teachers’ capacity to cope with the teaching/learning process to improve quality of education;

- Enhance better parenting to participate in managing and supporting educational initiatives;

- Build capacity of schools as institutions to handle additional number of drought-affected migrant children to attend schools.

There are no changes to SDRP projects in this sector.

### 3.2.5	AGRICULTURE AND LIVELIHOODS

| Indicator | Target | Achieved as of MTR |
| --- | --- | --- |
| Amount of seeds distributed | 9,000 MTs | 1,455 MTs of barley seeds and 7,665 MTs of wheat seeds |
| Number of beneficiary households for seeds distribution | 18,000 | 10,000 |
| Time frame of wheat and barley seeds distribution | In time for 2009/2010 planting season | December 2009 |
| Amount of animal feeds distributed | 9,450 MTs | 4,417 MTs |
| Number of beneficiary households for fodder distribution | 20,000 | 12,026 |
| Number of animals per household | 10 | 10 |
| Duration of the animal feed ration | Three months | Distribution of 50% of the planned ration began at the end of Nov ember 2009 |
| Average amount of micro-grants | $800 | No funding received |
| Number of beneficiary households receiving micro-grants | 5,000 | No funding received |
| Number of persons benefiting from business skills training/development | (target to be identified) | No funding received |
| National drought strategy implemented effectively | National drought- strategy implemented | No funding received |
| EWS coverage and efficiency enhanced | (target to be identified) | FAO will implement a project to expand the drought EWS to cover the whole territory and to strengthen the functional capacity and efficiency of the EWS Unit |
| Number of migrants who received assistance upon return | 40,000 | No funding received |

In coordination with MoAAR, other related government institutions and other NGO partners, FAO planned to assist up to 18,000 destitute farmers.  However, as the programme has been under funded and the sowing time will finish by the end of December 2009, the programme’s target was reduced to 10,000 destitute farmers in the most affected areas, with special focus given to those in the north-eastern governorates of Al Hassakeh, Ar Raqqah and Deir Ezzor.  Each beneficiary farmer will receive 300kg of high-quality seeds of local varieties of wheat and barley, plus smaller potential drought-tolerant crops, especially food legumes.  This will enable the cultivation of 30,000ha of land (an average of three hectares per beneficiary farmer).  The beneficiary farmers will be selected from those who have completely lost their harvests due to the drought in the three governorates and possess less than 10ha.  It is expected that the Government/MoAAR will support the remaining affected farmers.

The reduced quantity of seeds to be provided are expected to produce 60,000 MTs of wheat and barley, instead of 108,000 MTs planned earlier.  The produced quantities are sufficient to cover beneficiary households’ consumption needs of wheat (estimated at 170kg and 35kg per capita per annum for wheat and barley, respectively) and produce a surplus of 380kg of wheat or barley per beneficiary household.  The surplus could be sold on the market to generate a minimum of $230 of supplementary income per beneficiary farmer.  It is anticipated that the sale of the surplus will contribute to stabilizing local food prices.

SDRP sector objectives remain valid at the time of the MTR.  These objectives are:

- Build community resilience to drought;

- Support the livelihoods and household food security of the most destitute drought-affected farmers and herders;

- Mitigate the associated rise in food prices.

These objectives shall be achieved through:

- Ensuring that farmers in rain-fed areas can access seeds of local varieties of drought-tolerant wheat, barley and other potential crops for the 2009/2010 cropping season;

- Sustaining the remaining asset base of vulnerable small-scale herders by providing animal feed to the most destitute;

- Assisting with crop diversification, and water and soil appropriate management;

- Supporting creation of new income sources for most vulnerable farmers and herders, which could be agriculture or non-agriculture base;

- Assisting in building Government capacity to implement the prepared drought mitigation strategy and EWS;

- Helping migrants to restart their livelihoods in their areas of origin.

Changes to SDRP projects:

- The planting season is almost over and no funding (except for a CERF grant) has been received.  Therefore, requirements for the FAO project Emergency Response to Support Livelihoods and Food Security of the Destitute Farmers in the North-Eastern Governorates in Syria have been decreased from $4,989,450 to $3,164,620.  A total of $2,573,500 from the total amount is provided by CERF and other donors.  The Government of Syria provided $720,000.

- In addition, the IOM project Assisted Voluntary Return to Drought-affected Areas revised its requirements from $4,757,000 to $1,923,032.

The total revised requirements for this sector are $13,426,002.  The amount constitutes a 23% decrease from the initial amount.

# ANNEX I.	FULL PROJECT LIST AND FUNDING TABLES

| Project Code | Appealing Agency | Project Title | Original Requirements ($) | Revised Requirements ($) | Funding ($) | % Covered | Unmet Requirements ($) | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AGRICULTURE/LIVELIHOODS |
| SYR-09/A/25688/R/123 | FAO | Emergency Response to Support Livelihoods and Food Security of the Destitute Farmers in the North Eastern Governorates in Syria | 4,989,050 | 3,164,620 | 1,748,675 | 55% | 1,415,945 | Time-critical |
| SYR-09/A/25689/123 | FAO | Emergency Response to Support Food Security and Life Sustaining of the Destitute Small Herders in the North Eastern Governorates and the Badia | 7,400,000 | 7,400,000 | 348,675 | 5% | 7,051,325 | Time-critical |
| SYR-09/A/25691/123 | FAO | Capacity-building for Implementation of the National Drought Strategy | 462,200 | 462,200 | - | 0% | 462,200 | Stabiliza-tion and resilience |
| SYR-09/A/25692/R/123 | FAO | Development of a Drought Early Warning System | 433,333 | 476,150 | 476,150 | 100% | - | Stabiliza-tion and resilience |
| SYR-09/A/25694/R/298 | IOM | Assisted Voluntary Return to Drought-Affected Areas | 4,757,000 | 1,923,032 | - | 0% | 1,923,032 | Stabiliza-tion and resilience |
| SYR-09/ER/25693/776 | UNDP | Livelihoods Support for the Most Vulnerable Communities in the North Eastern Region | 2,333,333 | 2,333,333 | - | 0% | 2,333,333 | Stabiliza-tion and resilience |
| Sub total for AGRICULTURE/LIVELIHOODS | 20,374,916 | 15,759,335 | 2,573,500 | 16% | 13,185,835 |  |
| EDUCATION |
| SYR-09/E/25696/124 | UNICEF | Education support to Drought- Affected People in NE Syria | 675,000 | 675,000 | - | 0% | 675,000 | Immediate assistance |
| Sub total for EDUCATION | 675,000 | 675,000 | - | 0% | 675,000 |  |
| FOOD |
| SYR-09/F/25695/561 | WFP | Drought Relief Emergency Food Assistance | 27,275,100 | 22,330,337 | 5,418,368 | 24% | 16,911,969 | Time-critical |
| SYR-09/F/25697/6443 | Qatar Red Crescent | Provision of dry Food Ration to the Most Vulnerable Families | 1,653,000 | 1,653,000 | - | 0% | 1,653,000 | Immediate assistance |
| Sub total for FOOD | 28,928,100 | 23,983,337 | 5,418,368 | 23% | 18,564,969 |  |
| HEALTH/NUTRITION |
| SYR-09/H/25698/R/6443 | Qatar Red Crescent | Operation of Clinics, BHU & Mobile Clinics In Dayr Ezzor And Hassekah Provinces | 120,000 | 429,300 | - | 0% | 429,300 | Immediate assistance |
| SYR-09/H/25699/122 | WHO | Reducing the Morbidity and Mortality of Under-five Children Due to Measles and of the General Population Due to Communicable and Respiratory Diseases in the Drought-affected Areas | 588,500 | 588,500 | - | 0% | 588,500 | Immediate assistance |
| SYR-09/H/25700/124 | UNICEF | Monitoring the Nutrition Status of Under-five Children in Drought Area in North eastern Goverorates, and in Drought Migrants’ Settlements | 520,000 | 520,000 | 263,327 | 51% | 256,673 | Immediate assistance |
| Sub total for HEALTH/NUTRITION | 1,228,500 | 1,537,800 | 263,327 | 17% | 1,274,473 |  |
| WATER/SANITATION |
| SYR-09/WS/25701/124 | UNICEF | Providing Access for Improved Quality and Quantity of Clean Water for Affected Population at NE Region | 630,000 | 630,000 | - | 0% | 630,000 | Immediate assistance |
| SYR-09/WS/25702/776 | UNDP | Provision of Reverse Osmosis Units to Secure Sustainable Access to Clean Drinking Water to 15,000 People in Drought-Affected Areas | 502,900 | 502,900 | - | 0% | 502,900 | Immediate assistance |
| SYR-09/WS/25703/776 | UNDP | Rehabilitation of Roman Wells to Secure Sustainable Access to Clean Drinking Water to 45,000 People in Drought-affected Areas | 599,200 | 599,200 | 200,000 | 33% | 399,200 | Immediate assistance |
| Sub total for WATER/SANITATION | 1,732,100 | 1,732,100 | 200,000 | 12% | 1,532,100 |  |
| Grand Total | 52,938,616 | 43,687,572 | 8,455,195 | 19% | 35,232,377 |  |

# ANNEX II.	ACRONYMS AND ABBREVIATIONS

CERF	Central Emergency Response Fund

CFS	child-friendly school

EFSA	Emergency Food Security Assessment

EWS	early warning system

FAO	Food and Agriculture Organization of the United Nations

FTS	Financial Tracking Service

ha	hectare

IOM	International Organization for Migration

JNAM	Joint UN Needs Assessment Mission

kcal	kilocalorie

kg	kilogram

MoAAR	Ministry of Agriculture and Agrarian Reform

mm	millimetre

MoE	Ministry of Education

MoHC	Ministry of Health and Construction

MoH	Ministry of Health

MTR	Mid-Term Review

MTs	metric tons

NGO(s)	non-governmental organization(s)

PHC	primary health care

QRCS	Qatar Red Crescent Society

RUSF	ready-to-use supplementary food

SDRP	Syria Drought Response Plan

SPC	State Planning Commission (Government of Syria)

UN	United Nations

UNCT	United Nations Country Team

UNDP	United Nations Development Programme

UNICEF	United Nations Children’s Fund

WFP	World Food Programme

WHO	World Health Organization

# Footnotes

Joint United Nations Needs Assessment Mission (JNAM), 2009.

According to the MoAAR as for December 2009, some areas in the drought-affected region received eight times the rainfall as compared with last year.

Government agencies include: the State Planning Commission (SPC); the General Badia Commission; the Ministry of Education (MoE); the Ministry of Agriculture and Agrarian Reform (MoAAR); and the Ministry of Health (MoH).

All dollar signs in this document denote United States dollars.  Funding for this appeal should be reported to the Financial Tracking Service (FTS) at fts@reliefweb.int, FTS will display requirements and funding on this year’s CAP page.

JNAM, 2009.

Syria Drought Response Plan 2009.

International Institute for Sustainable Development, June 2009.

Syrian Association for Health Promotion and Development, UNICEF.  Participatory rural assessment for migrant communities in Rural Damascus due to drought in north-eastern areas, July 2009.

Demographic figures of the Central Bureau of Statistics 2008 indicate that children under age 5 account for 15.6% of the total population, and pregnant and lactating women account for 20% of the women over 18.

Up to November 2009, some 40,000 small-scale herders and their families living in the Syrian steppe had received WFP food assistance funded through the 2008 Syria Drought Appeal.

SPC official communication, July 2009.

Ministerial instructions - Prime Minister’s Office, 2009.

Small-scale farmer: owns 20ha or less at the fourth agro-zone area of rain-fed cultivated land.  Small-scale herder: owns less than 50 heads of livestock.

JNAM 2009.

# Text boxes

0

100

200

300

400

500

600

Al

Hassakeh

Deir Ezzor

Al Raqqa

Aleppo

Edlib

Hama

Homs

Rural

Damascus

Longterm

ave.

2007/08

2008/09

Map 1: Map of drought-affected areas in Syria, indicating areas where rains have failed for one, two or three consecutive years, and indicating the importance of assistance Al-Shaddadi district (Hassake Governorate) as one of the most vulnerable areas, affected by two years of failed rainfall.